## Moneycoach
User Story | Acceptance Criteria | Comments | Readiness | Timelines
As a user I am able to have a compiled code from picked from SVN/Nexus repo for a particular CR and deploy this without any manual intervention | This is to be done for a specified CR only | Will have to first look at SVN repo structure to get an idea. If CR based folders are maintained, then it will be quicker. But if CR based folders aren't maintained, then SVN repo must be restructured. | If structure is ready, then this can be done in half day. | 4th September 2019
| The code is security tested | SonarQube is installed but it needs a backend DB to support storing projects, analysis. Will need a DB created for sonarqube. | If Db is ready, then this is a half day job. | 9th September 2019
| Code compilation is done if no addressable failures | Will have to have a look at the project if its already using build tool or not. | It will take half a day to create build file if it is not there. | 4th September 2019
| Application is successfully deployed post Backup of existing war is carried out | We will install Jenkins agent in the target server. | Deployment script is ready. | 9th September 2019
| Application is brought-up post deployment and working successfully. | NA | Deployment script is ready. It will take care of this requirement. | 9th September 2019
As a user when I test the application post deployment the application must run its cycle without any manual intervention | test battery of Katalon is integrated and test cases which are failed are sent as mail | We will work the team to get a list of API test cases to be automated via suite execution. We will get IPs, API body, and API method. | Katalon Studio is available, and multiple test cases can be automated & executed via Jenkins. | 9th September 2019
| If the old was is to be deployed then option to rollback from Jenkins or otherwise is provided | NA | Rollback script is ready. | 9th September 2019
Might take time

## Integra
User Story | Acceptance Criteria | Comments | Readiness | Timelines
As AO I should be able to deploy the only the specified code(CMS) in environment | CMS has to be provided to the deployer example Jenkins in this case and also a provision for integration should exist from JIRA, as plan to move the team to JIRA based approach once the desired setup is place. CMS needs to be control input which will then deploy code | Need more clarity on this story
| If a same object is present then system should not deploy it | MSDeploy will ensure such checks are maintained. | Based on MSDeploy installation by WinAdmin
| If more than one distinct releases are there then these need to be deployed in FIFO sequence of the release | As discussed on 23/08/2019, this is done once all patches are moved to higher environment. We will write a python script to zip all the patches and apply them in proper sequence | Script must be written and tested internally | 2019-09-13
| Before deploying the system needs to back up the old object | CherryPicker can do this but it needs a release note which it will read and compare the items against items in a path. In this case, the path happens to be IIS site folder. | Ready with solution | 2019-09-04
| Release is provided in the same folder structure as is present in LIVE; Deployment should deploy the specified objects in the specified path only and take backup of the specified object and replace that with the new one. | MSDeploy along with CherryPicker will complete this story in tandem. | Ready with solution
| tool to identify If the folder is a new one then accordingly the folder will be copied with its content | Sync verb of MSDeploy would be used while copying files and folders from source to destination. If a folder is there in source but not in destination, then MSDeploy would copy the new folder to the source | Ready with solution
| If the code is app and DB; then DB to be deployed by DB tool and app by app tool | DB Deployment would be done via a separate Jenkins job | DB Project Readiness is a dependency
As AO I should be able to deploy the web-config release without any manual intervention | 4 Acs | Currenly, this story is in brainstorming stage. | Will provide a timeline

## Process
# | Steps
1 | Verification of JDK version present on the agent
1.1 | If JDK 1.8 is not there, then it must be installed
1.2 | If JDK 1.7 is there, then JDK version must be upgraded to 1.8 as Jenkins agent relies on JDK 1.8
1.3 | If JDK 1.8 is installed, but JAVA_HOME path isn't set, then it must be set by WINADM
2 | Connect Agent and Master
3 | Installation of build tool---Ant in the agent server
4 | Installation of build tool---MSBuild in the agent server
5 | Installation of MSDeploy (complete package) in the target server (Jenkins agent) ------- requires admin privileges
6 | Require information JDK version of the project
7 | Require information on .NET framework of the project